| World Trade Organization |  |
| --- | --- |
|  | G/SPS/GEN/1046 12 October 2010 |
|  | (10-5217) |
| Committee on Sanitary and Phytosanitary Measures |  |

UPDATE on THE OPERATION OF the Standards and

Trade Development Facility

Note by the Secretariat

# Overview

The Standards and Trade Development Facility (STDF) is a global programme in sanitary and phytosanitary (SPS) capacity building and technical cooperation established by the Food and Agriculture Organization of the United Nations (FAO), the World Organisation for Animal Health (OIE), the World Bank, the World Health Organization (WHO) and the World Trade Organization (WTO).  Other organizations - including the International Trade Centre (ITC), the United Nations Industrial Development Organization (UNIDO) and the United Nations Conference on Trade and Development (UNCTAD) – as well as donors and developing countries also participate in the Facility.

The STDF has two main aims:

- to assist developing countries enhance their expertise and capacity to analyze and implement international SPS standards, improving their human, animal and plant health situation, and thus ability to gain and maintain market access;  and

- to act as a vehicle for awareness raising on the importance of SPS issues, coordination among technical cooperation providers, the mobilization of funds, the exchange of experience and the dissemination of good practice in relation to the provision and receipt of SPS-related technical cooperation.

This document provides an overview of STDF activities since the previous SPS Committee meeting on 29-30 June 2010 in the following three areas of its Operating Plan:  (i) coordination and information dissemination;  (ii) project development;  and (iii) project funding.

# Coordination and information dissemination

## Pilot project on SPS indicators

In 2010, the STDF started work on SPS indicators to support the identification and application of indicators to measure the performance of national SPS systems.  In particular, this work has three main objectives:  (i) to sensitize the SPS community about the importance of managing for results and, more specifically, about the value and role of indicators;  (ii) to identify, pilot test and refine a representative set of indicators to measure the performance of a national SPS system;  and  (iii) to develop guidance materials to promote the use of indicators within results-based management frameworks for national SPS systems.  This work will contribute to, and support, other STDF activities to enhance the use of results-based management within SPS-related projects and programmes as well as broader efforts to monitor the impact of Aid for Trade by focusing on monitoring and evaluation of assistance at an operational, issue-specific level.

In this context, the STDF organized a technical working meeting on SPS indicators in Geneva on 1 July 2010, in collaboration with the Organisation for Economic Cooperation and Development (OECD).  Over 80 participants attended the meeting, including 16 experts from developing countries whose participation was funded by the STDF.  Participants discussed a draft STDF/OECD working paper on the topic and, in particular, a preliminary set of indicators.  The paper focused on the identification of indicators to track and measure performance of national SPS systems (macro level), based on the logical framework intervention logic and OECD terminology, i.e. inputs → activities → outputs → outcomes → impacts.  The STDF work does not undertake to develop indicators for particular SPS projects or programmes (micro level), which will obviously depend on the specific objectives of the intervention in question.

Participants agreed on the value of a results-based management approach to measure the performance of national SPS systems, and on the use of the logical framework in this context.  There was consensus at the meeting that one size does not fit all and that indicators should be adapted by countries depending on their particular circumstances.  The importance of ensuring synergies with FAO, OIE, IICA and other organizations that are applying capacity evaluation tools – which provide useful  baseline data – was underlined.  The identification and application of macro-level indicators is a long-term and iterative activity that is likely to require substantial time and resources from a range of stakeholders.  It was agreed to further refine and improve the indicators proposed through inputs from technical experts as well as pilot testing activities.

The STDF work on SPS indicators is a "work-in-progress".  The draft working paper has been revised on the basis of discussions at the meeting and is available on the STDF website (http://www.standardsfacility.org/TASPSindicators.htm).  A proposal to carry out pilot testing work on SPS indicators at country level will be discussed by the Working Group on 22 October.  SPS agencies in developing countries that are interested to participate in this exercise are encouraged to contact the STDF Secretariat (STDFSecretariat@wto.org).

## Workshop on public-private partnerships in the sps area

On 4-5 October 2010, the STDF organized a workshop in The Hague, The Netherlands, on the role of Public-Private Partnerships (PPPs) in enhancing SPS capacity, in close collaboration with the Netherlands Ministry of Agriculture, Nature and Food Quality (LNV) and the World Bank Institute.  Over 100 representatives from government agencies, international and regional organizations, donors, research institutes and the private sector participated in the workshop.  Thirty-one representatives from developing countries were funded by the STDF.  Participants engaged in a lively discussion on the policy considerations and implementation issues related to PPPs, considering their drivers and working modalities, challenges, innovations and good practices.  The workshop was followed by an excursion to the Port of Rotterdam on 6 October.  Representatives from the Port Authority and government inspectors made presentations about their work and illustrated what happens when large shipments of food and agricultural imports arrive in Europe.

The STDF is preparing a two-page briefing on the conclusions and recommendations of the  workshop as part of its regular series of STDF Briefing Notes.  In addition, a desk study is under preparation which will categorize and analyze relevant PPPs in the SPS area.  This study is expected to be available by the end of 2010.  Finally, all the presentations made at the workshop - as well as other relevant background information - are available on the STDF website (http://www.standardsfacility.org/TAPPP.htm).

## USE of economic analysis to inform sps decision-making

The STDF has initiated pilot testing work on the use of the multi-criteria decision analysis (MCDA) approach to inform decision-making on SPS capacity building and resource allocation.  This project was initiated following the STDF workshop on this topic in Geneva on 30 October 2009.  This work will first be implemented in two African developing countries.  In 2011, one developing country in Asia and one in Latin America will be included.  The project will assist in refining the MCDA approach and methodology to develop a set of practical tools for authorities responsible for food safety, animal and plant health, and trade.  A practical manual on the MCDA framework, as well as training materials on the application of the MCDA for use by developing country experts will be prepared.  Following the pilot testing exercise at the country level, three regional training workshops will be organized to equip SPS experts in each region with the knowledge and skills to apply the MCDA methodology.

## Regional SPS frameworks and strategies in Africa

The STDF published a scoping study, conducted at the request of the African Union Commission (AUC), in a first attempt to identify and assess the myriad of regional SPS policy frameworks and strategies in Africa and guide future work in this area.  The study is available on the STDF website (http://www.standardsfacility.org/IROthers.htm).  The study recommends the AUC and regional economic communities (RECs) to:  (i) ensure that regional policy frameworks focus on the most effective use of resources to enhance member states' benefits;  (ii) participate actively in the work of the international standard-setting bodies (Codex, OIE, IPPC) as well as the WTO SPS Committee, and develop the capacity for African countries to participate effectively in these mechanisms;  (iii) assist in strengthening and training of national SPS coordination bodies;  (iv) increase awareness of SPS matters at the political and general public level;  (v) focus capacity-building efforts on demand-driven activities, identified through SPS capacity evaluations, and involve all relevant stakeholders;  and (vi) avoid multiplication of transparency requirements and use existing tools developed by the SPS Committee.  A parallel scoping study on the establishment and functioning of national SPS coordination mechanisms in Africa is underway and scheduled to be completed in January 2011.

## Information dissemination activities

The STDF website (http://www.standardsfacility.org) has been redesigned, giving it a more contemporary look and making it more user-friendly.  New features have been added, either by improving existing functions or by adding new ones, and additional enhancements are underway.  STDF partners, donors, beneficiaries and the SPS international community at large are encouraged to increase their use of the STDF as a platform for the sharing and dissemination of information on SPS-related projects and initiatives.  The STDF has also created an e-mail distribution list to improve the dissemination of information about STDF activities and its latest publications (including the STDF newsletter).  If you are interested to register for this service, please visit the following link:  http://icd.wto.org/member/register.aspx?l=e and follow the instructions.  An article about the STDF entitled:  "Standards and Trade Development Facility:  A Collaborative Approach to Strengthen Sanitary and Phytosanitary Capacity" was published in International Trade Forum, ITC's quarterly magazine.

The STDF participated in and contributed to various internal and external meetings and events since the last SPS Committee meeting in June 2010.  These included a side-event on SPS capacity building on the margins of the African Agriculture Science Week (FARA) held in Ouagadougou, Burkina Faso (19-24 July) and a workshop in the context of the EU-funded Better Training for Safer Food (BTSF) programme in Cape Town, South Africa (12-14 October).  The latter was followed by a Steering Committee meeting of the PAN-SPSO project on 15-16 October.  The STDF also reported on its experiences and lessons learned at the WTO Transparency Workshop on 18 October 2010.

# Project development

Project preparation grants (PPGs) are a key mechanism in STDF programme development and help overcome constraints faced by developing countries in the articulation of their needs.  They also assist in ensuring synergies with other on-going initiatives, in particular Aid for Trade and the EIF, and in the mobilization of funds to implement activities.  A total of 42 PPGs have been approved and funded by the STDF since its inception.

At the STDF Working Group meeting on 2 July 2010, two PPGs were approved:

- STDF/PPG/323 – Enhancing the Safety and Quality of Agricultural Products in Senegal

- STDF/PPG/328 – Developing Trade Opportunities:  An Integrated Systems Approach for Pest Risk Management

# Project funding

A total of 46 projects have been approved for STDF funding since its inception.  On 2 July, the STDF Working Group approved three new projects for funding:

- STDF/PG/298 – SPS Capacity Building in Africa to mitigate the Harmful Effects of Pesticide Residues in Cocoa and maintain Market Access

- STDF/PG/319 – Strengthening the Food Safety Risk Assessment Unit in Colombia

- STDF/PG/326 – A Southeast Asian Partnership to Build Trade Capacity for Fresh and Processed Fruit and Vegetable Products.

An overview of the current status of STDF projects and PPGs is provided in the Annex.  Since its inception, the STDF has devoted 48 per cent of project resources to Least Developed Countries (LDCs) and Other Low Income Countries (OLICs), as shown in Figure 1 below.  Figure 2 indicates that 56 per cent of the number of STDF projects and PPGs has gone to Sub-Saharan Africa, 15 per cent to Latin America and the Caribbean, and 11 per cent to Asia.  In addition, 13 per cent of STDF projects and PPGs can be classified as global.

Applications for STDF funding can be made at any point in the year but should be received at least 60 working days in advance of each Working Group meeting in order to be considered at that meeting.  The next deadline for the submission of applications is 7 January 2011.  Applicants are strongly encouraged to read the "Guidance Note for Applicants" available on the STDF website.

ANNEX

IMPLEMENTATION STATUS OF STDF PROJECTS AND PROJECT PREPARATION GRANTS

STATUS OF APPROVED PROJECTS

#### Projects awaiting contracting

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PG/300 | Develop a combined e-learning curriculum and web-based information system for food standards | Develop a combined e-Learning curriculum and information system on food standards as a contribution to up-grading the quality infrastructure in developing countries | Ghana | TBC | 10-Dec-09 | TBC | TBC | $242,798 |
| STDF/PG/302 | Support to the cabbage sector in the Niayes Region of Senegal | Increase the production of cabbage and hence exports to the sub-region by controlling the spread and impact of two specific pests and assisting producers in meeting the Maximum Residue Limit established by Codex | Senegal | Senegal's Horticulture Union of the Niayes region (AUMN) | 19-Mar-10 | TBC | TBC | $273,895 |
| STDF/PG/318 | National program for the monitoring and integral management of contaminants in export product | Establish a comprehensive program to control residues of pesticides and mycotoxins and implement this program for two pilot exportable products | Ecuador | IICA | 19-Mar-10 | TBC | TBC | $431,710 |
| STDF/PG/319 | Strengthening the Food Safety Risk Assessment Unit in Colombia | Elaborate the functioning procedures of the Unit, establish its work programme and create a network of risk assessors to conduct future risk analyses | Colombia | IICA | 02-Jul-10 | TBC | TBC | $418,000 |
| STDF/PG/326 | A Southeast Asian partnership to build trade capacity for fresh and processed fruit and vegetable products | Develop a competency-based education and training platform for selected value chains and provide customized training using a combination of face-to-face instruction and e-learning | Thailand, Vietnam | MSU | 02-Jul-10 | TBC | TBC | $599,665 |

TBC:  To be confirmed

#### Ongoing projects

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PG/048 | Improving shea and cashew nut production in Benin through the application of good agricultural practice | Apply good agricultural practices to overcome problems of mycotoxin contamination in shea and cashew nut production | Benin | CRA- Agonkanmey (Centre de Recherches Agricoles d'Agonkanmey) | 07-Nov-07 | 01-Jun-08 | 15-Oct-10 | $455,575 |
| STDF/PG/062 | Strengthening food safety in Cameroon | Reactivate a national committee on food safety and train public and private sector stakeholders in Cameroon | Cameroon | FAO | 07-Nov-07 | 01-Sep-08 | 31-Dec-10 | $445,964 |
| STDF/PG/065 | Develop a private/public safety control system for the horticultural export sector in Guinea | Assist the public and private sector to meet official and commercial standards for fruit and vegetable exports through development of a safety control system. Project developed based on IF DTIS report | Guinea | UNCTAD | 06-Sep-05 | 01-Dec-05 | 30-Jun-10 | $530,300 |
| STDF/PG/108 | Developing institutional capacity of countries in the Americas to participate in the SPS Committee | Promote more active and effective participation in SPS Committee through a regional review of SPS compliance structures and practices | Latin America & Caribbean | IICA | 16-Oct-06 | 01-Oct-07 | 31-Jul-10 | $575,588 |
| STDF/PG/116 | Development and implementation of a traceability system in the livestock sector in Costa Rica | Develop a sustainable traceability system in the livestock sector which facilitates the management of information related to agricultural units and epidemiological events | Costa Rica | IICA | 10-Oct-08 | 01-Mar-09 | 28-Feb-11 | $455,220 |
| STDF/PG/126 | Establish the Horticulture Development Council of Tanzania | Assist the Tanzanian horticulture sector to address SPS issues | Tanzania | Tanzania Horticulture Association (TAHA) | 26-Jun-08 | 01-Jul-09 | 28-Feb-11 | $253,755 |
| STDF/PG/127 | SPS information system in Benin | Improve information flows on SPS requirements, particularly in the private sector in Benin | Benin | Benin Chamber of Commerce | 07-Nov-07 | 01-Sep-08 | 28-Feb-11 | $359,790 |
| STDF/PG/134 | Capacity building to improve fish trade performance of selected West African countries | Improve knowledge and awareness of SPS issues in the fisheries sector in five West African countries | Benin, Mauritania, Senegal, Sierra Leone and The Gambia | FAO | 02-Mar-07 | 01-Jun-08 | 30-Jun-10 | $469,000 |
| STDF/PG/155 | Nicaragua market oriented training service on market application of SPS | Establish SPS professional training units, to develop training manuals, quality and good process controls for pilot products | Nicaragua | IICA | 10-Oct-08 | 01-Jun-10 | 31-May-12 | $519,439 |
| STDF/PG/170 | Strengthening the capacity of government SPS officials in Nepal | Train government officials on implementation of SPS measures. Project based on IF DTIS | Nepal | FAO | 02-Mar-07 | 01-Apr-08 | 31-Jul-10 | $347,900 |
| STDF/PG/171 | Centre of Phytosanitary Excellence (COPE) | Build phytosanitary capacity and increase market access through the establishment of an East African Phytosanitary Centre | Kenya and East Africa | CABI (Centre for Agricultural Bioscience International) | 07-Nov-07 | 26-May-08 | 30-Nov-10 | $699,375 |
| STDF/PG/172 | Expanding exports of sesame seeds and sheanut/ butter through improved SPS capacity building for private and public sector | Identify critical control points and factors along the Nigerian shea nut production chain and develop predictive models for aflatoxin production and fungal growth, pesticide residues and other contaminants | Nigeria | Nigeria Export Promotion Council (NEPC) | 10-Dec-09 | 01-Oct-10 | 30-Sep-12 | $324,240 |
| STDF/PG/230 | Establishment of Pest Free Areas for Lethal Yellowing Disease (LYD) in Coconuts in Mozambique | Build phytosanitary capacity to implement international standards to manage LYD in palms and thereby expand market access for coconuts | Mozambique | FAO | 26-Jun-08 | 01-Jul-09 | 28-Feb-11 | $326,528 |
| STDF/PG/238 | Development of accredited HACCP certification schemes for processed food products | Implement accredited inspection and certificates for Good Manufacturing Practices and HACCP recognized by the competent authorities | Guatemala | AGEXPORT | 27-Feb-09 | 01-Feb-10 | 30-Jan-12 | $398,225 |
| STDF/PG/259 | Strengthening Vietnamese SPS Capacities for Trade | Strengthen Vietnamese SPS capacities for trade by improving safety and quality for fresh vegetables through the value chain approach | Viet Nam | FAO/Fruit and Vegetable Research Institute | 26-Jun-09 | 01-Mar-10 | 29-Feb-12 | $476,580 |
| STDF/PG/283 | Support for SPS risk assessment in the mango export sector | Improve Mali's capacity to comply with international and private SPS standards in the mango sector | Mali | Agence National de la Sécurité Sanitaire des Aliments (ANSSA) | 10-Dec-09 | 15-May-10 | 15-May-12 | $423,400 |
| STDF/PG/284 | Strengthening the National SPS Committee of Honduras | Strengthen the National SPS Committee of Honduras, further support the implementation of the National SPS Agenda (developed by the Committee) and consolidate and develop institutional SPS capacities | Honduras | Organismo Internacional Regional de Sanidad Agropecuaria (OIRSA) | 19-Mar-10 | 01-Jul-10 | 30-Jun-12 | $257,580 |
| STDF/PG/287 | Information sharing initiative on the actions to control fruit flies in Sub-Saharan Africa (SSA) | Facilitate the publication of a newsletter on fruit fly control in SSA which will feature on-going initiatives and inform about technical advances in the area | Sub-Saharan Africa | COLEACP (Comité de Liaison Europe-Afrique-Caraïbes-Pacifique pour la Promotion des Exportations horticoles ACP) | 27-Feb-09 | 01-Jun-09 | 30-Apr-11 | $82,800 |
| STDF/PG/298 | SPS capacity building in Africa to mitigate the harmful effects of pesticide residues in cocoa and to maintain market access | Build SPS capacity in Africa to produce good quality cocoa that complies with the relevant international regulations and legislation on pesticide residues and other harmful substances | Cameroon, Côte d'Ivoire, Ghana, Nigeria, Togo | International Cocoa Organization | 02-Jul-10 | 01-Jan-11 | 31-Dec-12 | $593,460 |
| STDF/PG/313 | Continuation of the West African Fruit Fly Initiative (WAFFI) in 2010 | Continue and deepen the regional sensitization and training work in eight countries in the sub-region | West Africa | CIRAD (Centre de Coopération Internationale en Recherche Agronomique pour le Développement) | 10-Dec-09 | 01-Apr-10 | 31-Mar-11 | $499,537 |

#### Completed projects

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PG/005 | STDF Database | Establish a database covering the period 2001-03 to:(i) help reduce duplication and gaps in activities; and (ii) track SPS-related technical assistance flows and trends | Global | S&H Switzerland | 01-Jun-03 | 01-Jul-03 | 01-Dec-05 | $45,100 |
| STDF/PG/009 | Model programme for developing food standards within a risk analysis framework | Strengthen capacity of low income countries in the Asia Pacific Region to develop food standards based on international requirements and participate in Codex | Asia Pacific countries | FAO | 01-Nov-03 | 01-Mar-05 | 01-Sep-06 | $70,848 |
| STDF/PG/010 | Support to pilot activities for national implementation of the International Portal on Food Safety, Animal and Plant Health in Turkey and Uganda | Establish national windows for IPFSAPH through training and the development of a handbook | Turkey and Uganda | FAO | 01-Nov-03 | 01-Mar-05 | 01-Sep-06 | $59,400 |
| STDF/PG/013 | Development of Regional Action Plans to Enhance Veterinary Capacity in East and West Africa | Develop regional strategies to strengthen veterinary capacity in East and West Africa with emphasis on improved surveillance, reporting, control and implementation of international standards | Mali, Ethiopia and Djibouti | OIE | 01-Sep-04 | 01-Oct-06 | 31-Jul-08 | $305,000 |
| STDF/PG/014 | Evaluation of capacity of national veterinary services | Develop a veterinary capacity evaluation tool based on the IICA Performance Vision Strategy document | Latin America & Caribbean | OIE | 01-Nov-03 | 01-May-04 | 01-May-06 | $39,960 |
| STDF/PG/015 | Expanding SPS capacities at national and regional levels | Develop a training programme and core group of trainers to deliver training for veterinary officials | OIE delegates from Mali, Thailand, Egypt, CIS and Latin America. | OIE | 01-Sep-04 | 01-Sep-04 | 01-Dec-07 | $130,614 |
| STDF/PG/019 | Model arrangements for SPS stakeholder involvement at the national level | Improve SPS-related information flows and information sharing between the public and private sector with positive spin-offs for market access | Sri Lanka and Paraguay | Abt Associates Inc. | 01-Sep-04 | 01-Dec-04 | 01-Apr-07 | $291,218 |
| STDF/PG/020 | Country-based plans for SPS-related development | Carry out baseline studies of SPS capacity and apply cost-benefit analysis to examine returns on investment in terms of foreign trade and an improved SPS situation | Peru and Uganda | Agra Ceas Consulting Ltd. | 01-Nov-03 | 01-Nov-04 | 01-Mar-07 | $170,862 |
| STDF/PG/037 | Assistance to developing countries in the implementation of International Standard for Phytosanitary Measure (ISPM) 15 | Train officials on implementation of ISPM 15 (Guidelines for regulating wood packaging material in international trade) to ensure minimal trade disruptions | 171 Delegates (79 countries and 6 regional organizations) attended workshop | IPPC, FAO | 01-Sep-04 | 01-Nov-04 | 01-Mar-06 | $332,000 |
| STDF/PG/056 | Capacity building to enhance implementation of the Codex Alimentarius Code of Practice on animal feeding | Strengthen implementation of good animal feeding practices and good manufacturing practices through development of training manuals, regional workshops in Africa, Latin America and Asia and country-level training | Feed industry in developing countries | IFIF (International Feed Industry Federation) | 09-Mar-05 | 01-Jun-05 | 01-Nov-06 | $150,000 |
| STDF/PG/069 | Improved capacity to ensure safety and quality of Yemeni seafood products | Assist the Yemeni Seafood Exporter's Association (YSEA) to improve the quality and safety of Yemeni seafood products | Yemen | YSEA (Yemeni Seafood Exporters Association) | 29-Jun-07 | 01-Aug-07 | 31-Dec-09 | $398,750 |
| STDF/PG/079 | Quality information on SPS issues – a prerequisite for capacity building | Improve the sharing of information on Codex, OIE and IPPC standards (and supporting scientific evaluations) through the International Portal on Food Safety, Animal and Plant Health (IPSAPH) | Developing countries | FAO | 06-Sep-05 | 01-Apr-06 | 30-Jun-09 | $435,185 |
| STDF/PG/089 | International Plant Health Risk Analysis Workshop | Enhance expertise and capacity of countries and NPPOs to conduct pest risk analysis (PRA) | 29 Officials from developing and least developed countries | FAO | 06-Sep-05 | 01-Oct-05 | 01-May-07 | $147,000 |
| STDF/PG/114 | Effective aflatoxin management system in Brazil nut production | Recover and consolidate export market access through implementation of an effective system to reduce aflatoxin contamination in the Brazil nut production chain | Brazil (Peru and Bolivia) | CIRAD (Centre de Coopération Internationale en Recherche Agronomique pour le Développement) | 03-Feb-06 | 01-Jun-06 | 30-Nov-08 | $619,664 |
| STDF/PG/120 | Risk analysis and risk assessment training in India | Enhance knowledge and skills of Indian officials on risk analysis and risk assessment procedures | India | *Manfred Luetzow, Regulatory Affairs Services GmbH *David Wilson * Canadian Food Inspection Agency | 03-Feb-06 | 01-Nov-06 | 31-Oct-07 | $95,060 |
| STDF/PG/133 | Building capacity to use the Phytosanitary Capacity Evaluation (PCE) Tool in the Pacific | Train National Plant Protection Organizations (NPPOs) in the South Pacific to evaluate their services using the PCE tool | South Pacific Forum Members | Secretariat of the Pacific Community | 16-Oct-06 | 01-Aug-07 | 31-Dec-09 | $179,000 |
| STDF/PG/145 | Rwanda Horticulture Export Standards Initiative (RHESI) | Increase Rwanda’s exports of fruit, vegetables and flowers in international and regional markets | Rwanda | Michigan State University (MSU) | 08-Jun-06 | 01-May-07 | 30-May-09 | $526,647 |
| STDF/PG/146 | Strengthening phytosanitary controls in Mali (with a focus on mango exports) | Expand international market access for fresh produce from Mali through improved phytosanitary control capacity. Project based on IF DTIS | Mali | Ministry of Trade (IF management unit) and FAO | 08-Jun-06 | 01-Jan-07 | 28-Feb-10 | $518,800 |
| STDF/PG/173 | Assessing capacity building needs of food control systems in developing APEC Member Economies | Train food safety regulators from developing member economies in Asia Pacific Economic Cooperation (APEC) using FAO's food safety capacity evaluation tools | APEC countries | FSANZ (Food Standards Australia New Zealand) | 02-Mar-07 | 01-Aug-07 | 30-Apr-09 | $97,500 |
| STDF/PG/246 | Development of SPS Action Plan for Cambodia | Identify actions to be taken to enhance the SPS system in Cambodia | Cambodia | FAO | 26-Jun-08 | 20-Apr-09 | 30-Jul-10 | $178,000 |
| STDF/PG/255 | Regional initiative on the fight against fruit flies in West Africa | Conduct tests in pilot mango orchards using different fruit fly control and other Integrated Pest Management techniques to monitor and control fruit fly populations in 8 pilot countries | Benin, Burkina Faso, Ghana, Guinea, Ivory Coast, Mali, Senegal, The Gambia. | CIRAD (Centre de Coopération Internationale en Recherche Agronomique pour le Développement) | 10-Oct-08 | 01-Apr-09 | 31-Mar-10 | $279,620 |

STATUS OF APPROVED PROJECT PREPARATION GRANTS (PPGs)

#### PPGs awaiting contracting

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PPG/316 | Strengthening phytosanitary inspection and diagnostic services in Azerbaijan | Strengthen the capacity of pre-border quarantine inspection points, notably through the provision of laboratory equipment and training of laboratory staff | Azerbaijan | TBC | 19-Mar-10 | TBC | TBC | $30,000 |
| STDF/PPG/323 | Enhancing the Safety and Quality of Agricultural Products in Senegal | Develop a project proposal to addresses the issue of pest surveillance and application of good agriculture practices to enhance Senegal's potential of horticultural exports | Senegal | TBC | 02-Jul-10 | TBC | TBC | $30,000 |

TBC:  To be confirmed

#### PPGs currently being implemented

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PPG/165 | Improving SPS controls in fruit production in Madagascar. | Assist Madagascar to establish pest-free places of production | Madagascar | CTHA (Centre Technique Horticole d'Antananarivo) | 07-Nov-07 | 01-Feb-08 | Upon approval | $20,000 |
| STDF/PPG/232 | A phytosanitary capacity building strategy for Africa | Improve phytosanitary capacity in African countries through the development and implementation of a phytosanitary capacity building strategy | Cameroon and other African countries | CABI (Centre for Agricultural Bioscience International) | 26-Jun-08 | 01-Dec-08 | Upon approval | $29,000 |
| STDF/PPG/262 | Strengthening veterinary services and promoting market access of animal products from Sahel countries to North African markets | Review a regional strategy to strengthen veterinary services | Mali, Niger, Burkina Faso | CILSS (Comité permanent inter-etats de lutte contre la sécheresse dans le Sahel) | 27-Feb-09 | 01-Dec-09 | 31-Jul-10 | $19,600 |
| STDF/PPG/268 | Harmonization of the legal, regulatory and institutional framework for an SPS control management system | Strengthen SPS-related legislation and improve the institutional management system | Tanzania | Natural Resources Institute (NRI)/ University of Greenwich John Eric Orchard | 10-Oct-08 | 01-May-09 | Upon approval | $20,000 |
| STDF/PPG/309 | Technical assistance to the Ministry of Trade and Industry to assist in the preparation of a project to build the SPS management system | Assist the Government in evaluating its bio-security situation through the application of the bio-security capacity evaluation tool developed by FAO | Guinea Bissau | Olivier Bertin-Mahieux | 10-Dec-09 | 15-Mar-10 | 30-Jun-10 | $30,000 |
| STDF/PPG/324 | Needs assessment and strategy for the development of Liberia's SPS system | Re-define Liberia's SPS framework by streamlining the number of ministries responsible for standards-related issues to a single national competent authority | Liberia | Londa Van der Wal | 19-Mar-10 | 01-Jul-10 | 30-Sep-10 | $30,000 |
| STDF/PPG/328 | Developing trade opportunities: an integrated systems approach for Pest Risk Management | Develop a transparent, mutually-agreed framework for considering the reduction of risk achieved by phytosanitary measures | Malaysia | Imperial College of Science, Technology and Medicine (ICL) | 02-Jul-10 | 06-Aug-10 | Upon approval | $30,000 |

#### Completed PPGs resulting in a project funded by the STDF

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PPG/062 | Develop a project proposal to strengthen SPS capacity in Cameroon | Apply the FAO/WHO "Guidelines to Assess Capacity Building Needs in Official Food Control Systems" | Cameroon | Jean Claude Cheftel, University of Montpellier | 01-Sep-04 | 09-May-05 | 31-Jul-05 | $20,000 |
| STDF/PPG/065 | Strengthen SPS capacity in Guinea | Develop a project proposal that builds on the UNCTAD evaluation of costs of compliance in the tropical fruit sector (based on IF DTIS) | Guinea | UNCTAD | 09-Mar-05 | 01-Jun-05 | 26-Aug-05 | $20,000 |
| STDF/PPG/069 | Develop a project proposal to strengthen SPS capacity in Yemen | Conduct a survey of SPS issues in the fisheries sector and project design (based on IF DTIS) | Yemen | Tim Huntington | 09-Mar-05 | 01-Oct-05 | 19-Nov-05 | $19,700 |
| STDF/PPG/088 | Strengthening SPS human resource capacity | Conduct evaluation of the training needs of Nepal's SPS authorities and design a training programme | Nepal | FAO | 06-Sep-05 | 01-Jan-07 | 27-Mar-07 | $20,000 |
| STDF/PPG/102 | SPS constraints and export diversification project preparation grant | Enhance SPS capacity in the fruit and vegetable sector | Mali | Malika Bounfour | 06-Sep-05 | 15-Mar-06 | 31-May-06 | $20,000 |
| STDF/PPG/103 | Rwanda Horticulture Export Standards Initiative (RHESI) | Enhance SPS capacity in the fruit and vegetable sector | Rwanda | Michigan State University (MSU) | 06-Sep-05 | 15-Feb-06 | 01-May-06 | $22,000 |
| STDF/PPG/116 | Establishment of a traceability system for the livestock sector in Costa Rica | Assist in the development of the animal health directorate's National Epidemiological Surveillance Programme by introducing a traceability system for livestock farms | Costa Rica | Emilio Leon | 03-Feb-06 | 01-May-07 | 15-Oct-07 | $20,000 |
| STDF/PPG/126 | Assistance to establish a horticulture industry organization in Tanzania | Develop a business plan and facilitate the establishment of a horticulture association in Tanzania | Tanzania | Tanzania Horticulture Association (TAHA) | 03-Feb-06 | 15-Jul-06 | 30-Sep-06 | $5,500 |
| STDF/PPG/127 | Strengthening the capacity of the Benin Chamber of Commerce to track SPS-related development in exports markets | Establish an information centre within the Benin Chamber of Commerce to ensure that firms are aware of SPS measures affecting their existing or planned exports | Benin | Stefan Skrzypczak | 08-Jun-06 | 20-Nov-06 | 28-Feb-07 | $20,000 |
| STDF/PPG/155 | Nicaragua market-oriented training service on standards application | Survey Nicaragua's SPS requirements in the plant health sector to improve export competitiveness | Nicaragua | Michigan State University (MSU) | 16-Oct-06 | 01-Mar-07 | 30-Oct-07 | $20,000 |
| STDF/PPG/171 | Centre of Phytosanitary Excellence (COPE) | Revise a project document to establish a Phytosanitary Centre of Excellence in Kenya. If funded the project would address issues raised in the IF DTIS reports for Uganda, Tanzania and Rwanda | Kenya | Ralf Lopian | 02-Mar-07 | 15-Apr-07 | 30-Nov-07 | $20,000 |
| STDF/PPG/172 | Expanding Nigeria’s food exports through enhanced SPS capacity | Enhance Nigeria's capacity in the SPS area and improve the country's ability to export high-value food products | Nigeria | CARANA Corporation | 02-Mar-07 | 01-Nov-07 | 31-Mar-08 | $25,000 |
| STDF/PPG/298 | Capacity building programme on pesticide residues and other harmful substances in cocoa in Africa | Assist cocoa-producing countries in Africa to produce cocoa that meets the food safety requirements of the EU, the USA and Japan | Cameroon, Côte d'Ivoire, Ghana, Nigeria and Togo | International Cocoa Organization | 26-Jun-09 | 12-Oct-09 | 31-Mar-10 | $30,000 |
| STDF/PPG/302 | Support the competitiveness of cabbage in the Niayes region | Improve the quality of cabbage by putting in place systems which will follow GAP schemes, facilitate traceability and HACCP | Senegal | Olivier Bertin-Mahieux | 26-Jun-09 | 01-Oct-09 | 31-Dec-09 | $25,631 |

#### Completed PPGs resulting in a project funded or seeking funding from other sources

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PPG/052 | Post-harvest contamination in Malawi and Zambia | Develop a project proposal to address post-harvest contamination problems in the paprika and groundnut sectors in Malawi and Zambia (based on IF DTIS) | Malawi and Zambia | Gordon Shephard | 09-Mar-05 | 15-Feb-07 | 15-Aug-07 | $20,000 |
| STDF/PPG/066 | Develop a project proposal to strengthen SPS capacity in Mozambique | Develop a project proposal that builds on the UNCTAD evaluation of costs of compliance in the tropical fruit sector. (based on IF DTIS) | Mozambique | UNCTAD | 09-Mar-05 | 23-May-05 | 26-Aug-05 | $20,000 |
| STDF/PPG/100 | Strengthening the national food control system for the fisheries sector in Cape Verde | Assist the fish processing sector in Cape Verde to comply with international food safety standards | Cape Verde | WTO | 29-Jun-07 | 07-Dec-06 | 31-Jan-07 | $27,737 |
| STDF/PPG/105 | OIE STDF project on the implementation of compartmentalization for avian influenza and Newcastle disease in the poultry sector | Design a demonstration project on how to apply compartmentalization | Brazil and Thailand | OIE | 29-Jun-07 | 22-Feb-08 | 01-Oct-08 | $20,000 |
| STDF/PPG/113 | Survey of food safety needs in Burundi | Apply the FAO/WHO "Guidelines to Assess Capacity Building Needs in Official Food Control Systems" to survey the food safety situation in Burundi and develop a trade-related project proposal | Burundi | WTO/ Burundi Standards Bureau Mohammed Majdi | 03-Feb-06 | 01-Sep-06 | 30-Nov-06 | $20,000 |
| STDF/PPG/191 | Enhancing Sierra Leone's national SPS capacity | Design a national SPS framework | Sierra Leone | CARANA Corporation | 29-Jun-07 | 01-Jan-08 | 31-Jul-08 | $20,000 |
| STDF/PPG/221 | Improving the competitiveness of suppliers in Burkina Faso's national, regional and international markets | Identify specific SPS issues and constraints affecting sesame production and exports and develop a project proposal to overcome these constraints and improve market access | Burkina Faso | Tidiane Traore | 04-Apr-08 | 10-Jan-09 | 30-Apr-09 | $20,000 |
| STDF/PPG/223 | Strengthening the official food control programme to support an emerging food business sector | Assess requirements to strengthen official food controls, standards and food inspection based on specific priority commodities identified in the World Bank Action Plan and develop a proposal for follow-up | Moldova | Enrico Casadei | 04-Apr-08 | 20-Jul-08 | 31-Oct-08 | $21,765 |
| STDF/PPG/234 | Design of Lao P.D.R Good Agricultural Practice scheme | Create institutional infrastructure to ensure market access for agricultural products from Lao PDR | Lao PDR | Andrew Wilson | 26-Jun-08 | 18-Aug-08 | 16-Jan-09 | $18,410 |
| STDF/PPG/242 | Elaboration of SPS needs expressed in the IF DTIS of Comoros | Assess SPS human resource and infrastructure needs based on the IF DTIS and formulate a project proposal to improve the competitiveness of the litchi and lobster sectors | Comoros | Chokri Damergi | 26-Jun-08 | 01-Feb-09 | 30-Apr-09 | $20,000 |
| STDF/PPG/286 | Accessing new ornamental plant market by reducing phytosanitary issues through participatory research and extension: the Clean Stock Programme in Costa Rica | Reduce the phytosanitary risk of exporting 5 varieties of ornamental plants in order to maintain access to the US market | Costa Rica | CATIE (Centro Agronómico Tropical de Investigación y Enseñanza of Costa Rica) | 27-Feb-09 | 15-May-09 | 31-Dec-09 | $30,000 |
| STDF/PPG/303 | Project preparation grant to conduct a total diet study for Sub-Saharan Africa | Elaborate a manual describing a methodology to conduct a regional TDS to evaluate the risks of chemical contamination of food | Sub-Saharan Africa | Centre Pasteur du Cameroun | 26-Jun-09 | 12-Oct-09 | 31-Mar-11 | $20,000 |
| STDF/PPG/305 | Institutionalising SPS for agricultural health and food safety systems in Africa | Conduct a scoping study to inform and assess the necessity of further action needed in the SPS area at the level of the AUC and the Regional Economic Communities | African Union | João Manuel GA de Magalhães | 26-Jun-09 | 01-Oct-09 | Upon approval | $30,000 |

#### Completed PPGs which have not been approved for funding

| Ref. No. | Title | Objective | Beneficiary | Implementing entity/ person | Approval date | Start Date | End Date | Budget (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STDF/PPG/038 | Agricultural Health and Food Safety Laboratory Needs Assessment for CARICOM Countries | Survey laboratory capacity in CARICOM to develop a project to assist in development of a regional strategy on laboratory infrastructure | Caribbean | CARICOM | 01-Sep-04 | 11-Oct-05 | 01-Jun-06 | $20,000 |
| STDF/PPG/046 | Implementation of Codex standards (WHO Africa) | Assist WHO Africa to develop a project proposal to support selected African countries to implement Codex standards | Benin and Tanzania | Kenza Le Mentec J. Claude Cheftel | 03-Feb-06 | 01-Aug-06 | 31-Aug-07 | $19,000 |
| STDF/PPG/061 | Strengthening SPS capacity in Cambodia | Conduct fieldwork in Cambodia to develop a project proposal | Cambodia | Digby Gascoine | 09-Mar-05 | 24-Apr-05 | 22-Jul-05 | $20,000 |
| STDF/PPG/063 | Quality control for agricultural products in Benin | Apply the FAO/WHO "Guidelines to Assess Capacity Building Needs in Official Food Control Systems" | Benin | Lois C. Laleye | 09-Mar-05 | 15-Jun-05 | 31-Jul-05 | $20,000 |
| STDF/PPG/064 | Strengthen SPS capacity in Djibouti | Conduct field research and design of project in the livestock sector in Djibouti (based IF DTIS) | Djibouti | Greg Sullivan | 09-Mar-05 | 25-May-05 | 01-Aug-05 | $20,000 |
| STDF/PPG/101 | Capacity evaluation of national food control system in Eritrea | Apply FAO/WHO "Guidelines to Assess Capacity Building Needs in Official Food Control Systems" and design a project proposal | Eritrea | Arpad Ambrus | 06-Sep-05 | 05-Jan-06 | 31-Mar-06 | $28,690 |

__________

# Footnotes

This document has been prepared under the Secretariat's own responsibility and is without prejudice to the positions of Members or to their rights or obligations under the WTO.

More detailed information on the STDF and its activities can be found on the STDF website (http://www.standardsfacility.org).

More information on the workshop, including the presentations and Guidelines on the Use of Economic Analysis to Inform SPS-related Decision-Making is available on the STDF website (http://www.standardsfacility.org/TAEcoAnalysis.htm).  The findings and conclusions from the workshop are summarized in STDF briefing note No. 3 (December 2009).

The STDF aims to devote at least 40 per cent of Facility project resources to LDCs and OLICs.